## ICF (hidden)
C3 - Uses MEI | Please provide the date the information in MassEnergyInsight was last verified. By including a date, you are confirming that the information in MEI is accurate and complete (including all fuels and renewable energy) and that you wish to report your Green Community annual energy usage directly through MEI. REMEMBER to load all diesel, gasoline, heating oil and propane energy usage, as well as renewable energy usage that is NOT virtually net-metered, into MEI prior to providing a date that your data is complete. Also, confirm that Table 3 in MEI matches the data provided in Table 2.
C3 - No MEI | Please complete “Crit 3 - Tbl 3 Non-MEI User Only."
RSD | To include a percentage of the energy use of a Regional School District, please include that prorated usage as a separate entry in lines 17 and 21 of Table 2: Enter here the % you are using to prorate the energy usage (i.e. the percentage of the RSD funding that the municipality contributes). Contact your Regional Coordinator if you need assistance.
EMS | Your EMS annual report may be used to fulfill your Green Communities Annual Report Table 4 requirement. Please provide the date it was filed with DOER, or the date it will be filed if filing is anticipated in the next six months. Other efficiency measures undertaken independently of the performance contract should be reported using Table 4. All other portions of the Green Communities Annual Report must be completed.
Bld Stck Chg | Please describe any building stock changes that have occurred since your last Annual Report, or Designation Appliction (if first Annual Report). Include the year and whether any changes are a replacement, addition, removal or renovation. The adjustments to energy usage should be entered on Table 2, Lines 16 and 20. You may use the Building Stock Changes Calculator provided.

## General Instructions
GREEN COMMUNITY ANNUAL REPORT
Annual Report Tab Coloring Key
Community input required
Examples
Guidance
1) In order for a municipality to maintain its Green Community Designation and be eligible for the next available Green Communities Competitive Grant, reports must be submitted no later than 5:00 PM November 6, 2020 for the reporting period July 1, 2019 – June 30, 2020
Late reports WILL deem a community ineligible for the 2021 Competitive Grant.
2) Please be certain to address all areas in full. If certain requested information does not apply, then please note it as “N/A."
3) Please follow the instruction for reporting on each Criteria on the individual Criterion Excel Sheets.
4) If you have any questions on these reporting requirements, contact your DOER Green Communities Regional Coordinator (RC). The objective is to have a dialogue with Green Communities staff BEFORE the report is due so that minimal follow-up with the municipality is required after the due date.
5) Submit your community's full Excel file electronically as Excel via email with any other supporting files to Grant Administrator Jane Pfister - jane.pfister@mass.gov and your Regional Coordinator. This page must be signed, made into a PDF, and submitted as a separate file. Please submit only one Excel file for the annual report. DOER will not accept multiple spreadsheets
6) NOTE: In the case of any criteria violations( e.g. a vehicle purchased that does not meet the fuel efficient vehicle policy), the municipality will be asked to provide a corrective action plan. A first-time violation will be factored into consideration when DOER awards funds under the next available Green Communities funding opportunity. A second violation may prohibit the municipality from being eligible for any funds in the next available Green Communities funding opportunity.
8) Fields highlighted in yellow should be completed by Green Communities.
9) Review the "AR Compliance Checklist" tab and ensure that no items are missing. If any items cannot be provided please offer an explanation.
Annual Report is complete.
Date Designated: | 2017-02-01 | PLEASE NOTE: For a municipality designated December 2018, the reporting period is 18 months, Jan 1, 2019 - June 30 2020
Date of Annual Report Submission
Name of Preparer of Annual Report | Fred Davis
Title | Chair, Medfield Energy Committee
Municipality Name | Town of Medfield
I confirm that I have reviewed this report and verify all information is true.
Signature of Chief Executive Officer |  | The Chief Executive Officer is defined as the manager in any city having a manager and in any town having a city form of government, the mayor in any other city, and the board of selectmen in any other town unless some other officer or body is designated to perform the functions of a chief executive officer under the provisions of a local charter or laws having the force of a charter. Any signatures of designees will be considered an attestation that the signatory has been designated the designee by the municipality.

## AR Compliance Checklist
GREEN COMMUNITY ANNUAL REPORT
Required Values
All values that are required to be reported in this annual report are listed here. If an input appears in red, the "Note" column will explain which cell or cells are missing a value. Click the input item name to go to the item in the corresponding input tab. Prior to submitting this annual report please review this tab to make sure no required items are missing. If any item cannot be completed, please provide an explanation.
<Select YES or NO>
Yes
No
Inputs
Overall Annual Report Status | Annual Report is complete
Tab | Item | Status |  | Note | Explanation
Crit 1 & 2 | Type of as-of-right siting approval received | Complete | 0
| Type of expedited permitting approval received | Complete | 0
| 1) Have any significant changes been made to the zoning district(s) for which the community received Green Communities designation? | Complete | 0
| 2) Have any significant changes been made to site plan, design, or other development review criteria or any permit review procedures that would impact the ability to permit qualifying clean energy uses as-of-right and in a timely manner? | Complete | 0
| 3) Since your last Annual Report, or Designation Application (if first Annual Report) have any clean energy projects applied for approval under the zoning for which the community received Green Community Designation? Have any clean energy project been approved for construction? | Complete | 0
| Table 1 | Complete | 0
Crit 3 - Overview | Is Regional School District (RSD) energy included? | Complete | 0
| What is the name of the RSD? | Complete | 0
| How is RSD energy included? | Complete | 0
| % or names of RSD building energy included | Complete | 0
| Does the community use MEI? | Complete | 0
| Date MEI was last verified | Complete | 0
| Does the community use an EMS Agreement? | Complete | 0
| Date EMS filed with DOER | Complete | 0
| Does the community use conventionally net meter renewable energy produced within the community? | Complete | 0
| Brief narrative of changes seen and anticipated. | Complete | 0
| Has the community had any building stock changes since it's baseline year? | Complete | 0
| Have any building stock changes occurred since your last Annual Report? | Complete | 0
| Building stock change narrative | Complete | 0
Building Stock Change Calculator | Building stock change calculator complete for all building stock changes that have occurred since the baseline year | Complete | 0
Crit 3 - Table 2 Progress | Does the Community use Calendar Year (CY) or Fiscal Year (FY)? | Complete | 0
| Baseline Year | Complete | 0
| Building Stock Change Adjustment - Current year | Complete | 0
| Regional School Prorated - Baseline year | Complete | 0
| Regional School Prorated - Current Year | Complete | 0
| TOTAL ENERGY CONSUMPTION (NO Weather Normalization) - Baseline year | Complete | 0
| TOTAL ENERGY CONSUMPTION (NO Weather Normalization) - Current year | Complete | 0
| Weather Normalized Consumption (without building stock adjustment) - Baseline year | Complete | 0
| Weather Normalized Consumption (without building stock adjustment) - Current year | Complete | 0
| Building Stock Change Adjustment (weather - normalized) - Current year | Complete | 0
| Regional School Prorated (weather-normalized) - Baseline year | Complete | 0
| Regional School Prorated (weather-normalized) - Current year | Complete | 0
Crit 3 -Tbl 3 for Non-MEI Users | Select plan year | Complete | 0
| Subtotal for buildings | Complete | 0
| Total energy consumption | Complete | 0
Crit 3 - Table 4 ECMs | Enter at least one ECM | Complete | 0
Crit 3 - Table 5 RE | If the community uses renewable energy, complete Table 5 | Missing | 0 | Please complete Table 5 | Filled in table- unclear why still showing up as missing.
Crit 4 - Vehicle Policies | 1) Replaced an exempt or non-exempt vehicle? | Complete | 0
| 2) Acquired a new exempt or non-exempt vehicle, and/or conducted inter-departmental vehicle transfers? | Complete | 0
| 3) Installed an electric vehicle charging station? | Complete | 0
| 4) Installed idle-reduction technology on any vehicles? | Complete | 0
| 5) Implemented anti-idling technology and/or campaigns? | Complete | 0
| 6) Implemented a driving monitoring system that records miles driven and/or fuel consumption? | Complete | 0
| 7) Implement a fuel use reporting system for operators on fuel efficiency ? | Complete | 0
| 8) Implement any other policies and/or technologies not listed above? | Complete | 0
| Narrative for #8 | Complete | 0
| 9) Does the community met Criterion 4 through alternative compliance? | Complete | 0
| Narrative for #9 | Complete | 0
| 10) For communities that met Criterion 4 through alternative compliance, provide as a status regarding the success of these programs and policies. | Complete | 0
Crit 4 - Vehicle Inventory | If the community replaced an exempt or non-exempt vehicle during FY fill out Table 6 (Acquistions and Retirements) | Complete
| If the community has acquired a new vehicle or transferred a vehicle in the FY fill out Table 6 (Acquisitions) | Complete | 0
Crit 5 - Stretch Code compliance | Is the stretch code still in effect? | Complete | 0
| Were any residential occupancy permits issued since your last Annual Report or Designation Application (if first Annual Report)? | Complete | 0
| How many occupancy permits were issued for new commercial construction over 100,000 sq.ft.? | Complete | 0

## Crit 1 & 2
Criteria 1 and 2
Type of as-of-right siting approval received: |  |  |  |  | Generation; Solar
Type of expedited permitting approval received: |  |  |  |  | Local
REGULATIONS (zoning & permitting): 1) Since your last Annual Report, or Green Communities Designation Application (if first Annual Report) Have any significant changes been made to the zoning district(s) for which the community received Green Communities designation? Significant changes, such as changes to the geographic extent of the district, allowed uses, and dimensional requirements, would impact the ability to construct a qualifying clean energy use in the district. Overlay districts, such as water protection districts that impose special permitting requirements, count as significant changes. If yes, submit the same documentation required for designation for CR1 to verify that you still meet the requirements (applicable sections of the zoning by-law, definitions, as well as a revised zoning map.) Select YES or NO in the dropdown on the right. | [7 empty] | NO
2) Have any significant changes been made to site plan, design, or other development review criteria or any permit review procedures that would impact the ability to permit qualifying clean energy uses as-of-right and in a timely manner? Significant changes would be anything that pertains to the “by-right” nature of the zoning or to the amount of time necessary to review required permits. If yes, attach a letter from municipal counsel that describes the changes, illustrates any potential impact on the siting of clean energy projects, and affirms continued compliance with the Green Communities As-of-Right Zoning and Expedited Permitting criteria. Select YES or NO in the dropdown on the right. | [7 empty] | NO
NARRATIVE: No changes were made in FY20.
PERMITTING:
3) Since your last Annual Report, or Designation Application (if first Annual Report) have any clean energy projects applied for approval under the zoning for which the community received Green Community Designation? Have any clean energy project been approved for construction? | [7 empty] | NO
Select YES or NO in the dropdown on the right. If YES, fill out or update Table 1 below:
Table 1 Expedited Permitting Projects During Reporting Year (Please add rows as required)
Click here to view a sample version of this table.
PROJECT NAME | Type (Generation (Capacity), R&D, and/or Manufacturing) | As-of-right designated location | Applicant | Project Description | Status | Date Submitted | Decision Date
To insert additional rows, select this row, right-click, and select "Insert."

## Crit 1 & 2 - Table 1 Sample
Click here to return to Table 1
Table 1: SAMPLE Expedited Permitting Projects
PROJECT NAME | Type (Generation (Capacity), R&D, and/or Manufacturing) | As-of-right designated location | Applicant | Project Description | Status | Date Submitted | Decision Date
Hilltop Wind | Renewable Energy (wind) 9 MW | landfill | Peak Performance, LLC. | Six 1.5 MW wind turbines on 16 acres of land | Project approved | 2016-11-01 | 2018-01-21

## Crit 3 - Overview
Criterion 3 Instructions: Complete Steps 1-7 Below
1. Read and complete all questions below.
2. Complete Table 2: Progress |  | Go to Table 2
Complete Table 2 for baseline year and reporting year, located 3 tabs to the right. ALL categories are required, with the exception of open space.
Fuel use from all vehicles, including those characterized as exempt AND non-exempt under Criterion 4, must be included.
Renewable Energy is a fuel source and the amount of renewable energy consumed by the Green Community must be included.
If you are using MEI. note that there is a report available (entitled Annual Report Table 2). This contains the data you need to enter into Table 2 . Please review the data in MEI and, if accurate, enter it into Table 2, located 3 tabs to the right. Note also that if you click on the "years" down arrow on that MEI report, you can choose which year is your baseline year.
Regional School District
Does the community include energy from a Regional School District in their total energy consumption? |  |  |  | No
3. Complete Table 3: Energy Use (NON-MEI Users) |  | Go to Table 3
Does the community use MassEnergyInsight (MEI) to provide data for Table 2? |  |  |  | Yes
Please provide the date the information in MassEnergyInsight was last verified. By including a date, you are confirming that the information in MEI is accurate and complete (including all fuels and renewable energy) and that you wish to report your Green Community annual energy usage directly through MEI. REMEMBER to load all diesel, gasoline, heating oil and propane energy usage, as well as renewable energy usage that is NOT virtually net-metered, into MEI prior to providing a date that your data is complete. Also, confirm that Table 3 in MEI matches the data provided in Table 2. |  |  |  | 2020-11-04
4. Complete Table 4: Energy Conservation Measures (ECMs) |  |  | Go to Table 4
Update your ECMs in Table 4 by: 1) listing measures that were completed since you submitted last Annual Report or Green Communities Designation as applicable, 2) listing new measures planned or in progress, 3) and providing an ECM type in Column F. All ECMs should be included in Table 4, NOT only ECMs funded by Green Communities grants.
Does the community use an Energy Management Services (EMS) Agreement? |  |  |  | No
5. Complete Table 5: Renewable Energy Projects |  | Go to Table 5
Update your conventionally net-metered (aka "behind the meter") RE projects in Table 5 by: 1) changing any status dates, and 2) adding any new RE projects. | Does your Green Community use any energy produced by renewable energy within your community? For example, solar PV systems installed on school or municipal buildings and the building uses the electricity generated, or a biomass boiler installed in a municipal building . Please select YES or NO in the dropdown on the right. if YES, complete Table 5 and be sure to include the renewable energy consumed in the building's MassEnergyInsight account or whatever energy tracking tool your community uses |  |  | YES
6. Provide a Narrative
Provide a brief narrative explaining changes seen and what is anticipated for the next year. Any notes on successes or challenges are welcome. Also include changes in building operating hours as well as building use, and/or significant changes in municipal fleet operations. Identify top 3 buildings in terms of energy consumption and note how efficient these buildings are by reporting their kBtu/sf numbers. MEI users can find this information by looking at the "Buildings to Target" report; provide a brief statement addressing change in the past year and, if applicable, describe plans for improving building performance next year | Sample Narrative: Our buildings have a 12 percent decrease in energy use and the vehicles have a 4 percent reduction. We are also intending to implement a large retrofit at the drinking water treatment plant this year that should yield a significant level of savings. We are seeing an uptick in energy use in our library, now that it open 10 more hours a week. Our top 3 energy-using buildings are our high school (68 EUI), middle school (88 EUI) and town hall (78 EUI). Energy use in all three buildings has been fairly consistent over the past year. The middle school boiler has reached the end of useful life and is scheduled to be replaced in 2 years. We have implemented projects in the Town Hall and would have expected larger savings. We are investigating this.
NARRATIVE:
The Town has made energy reductions across several categories in FY20 including buildings, streetlights, and water/sewer for a total reduction of 22.1% (or 14.7% with weather normalized data). This past year we implemented interior LED lighting projects in the schools (high school, middle school, and elementary schools). This combined with COVID-caused school closures in the spring have led to a significant reduction in energy use. However, the Town did use the opportunity of schools being closed to do deferred maintenance, so they were not completely shut down during this time. We also saw a substantial reduction of energy usage from streetlights due to an LED light retrofit completed in June 2019. The buildings with the highest energy usage per square foot include the Pfaff Center (recreation center) at 87.93 kBtu/sf, the Dale Street Elementary School at 84.39 kBtu/sf, and Medfield Highschool at 82.90 kBtu/sf. Please note that as a result of some faulty billing from Eversource, the total reduction does not show correctly in MEI: FY2020 only shows a 12.6% decrease in kwh of electricity. However, after offsetting refunds in billing, MEI does show $31,000 savings in spending in FY2020, in the range of 70% reduction annually. Energy consumption now seems correct starting April 2020: so comparing just the six months Apr-Sep, we see a 74% energy reduction between 2019 and 2020; this is likely the correct energy savings level. Medfield has completed many of the ECMs from our ERP and have a robust list of ECMs to implement over the next 5 years which we plan to get energy audits on this winter. Projects include weatherization and HVAC work in the school buildings, as well as work at the Town Hall and, Council on Aging, and Library. ECMs in Table 4 that don't have audit information are proposed measures that are in addition to the ERP.
7. Building Stock Changes
Has the community had any building stock changes since it's baseline year? |  |  |  | Yes
Please complete the Building Stock Change Calculator. Include all building stock changes that have occurred since the baseline in the current year.
Have any building stock changes occurred since your last Annual Report or Designation (if first Annual Report)? |  |  |  | No
As noted in the previous Annual Report building stock changes were done in FY2018 when the police station and fire station combined. Square foot adjustments are made in the calculator to reflect this change.

## Building Stock Change Calculato
INSTRUCTIONS on how to calculate your prorated energy use for building stock changes
All building stock changes that have occured since the baseline year should be reported here. Please keep track of the prorated use for every year you are reporting on. If you submitted an Annual Report last year, you only need to report on this current reporting year. If this is your community's first Annual Report, enter the building information for this reporting year and past years as needed. If your community did not submit an Annual Report last year, report on last years' building stock changes as needed.
USE THIS CALCULATOR FOR ALL BUILDING STOCK CHANGES
This Building Stock Changes Calculator is for both new buildings and building additions. Different information is to be entered depending on whether you are entering data for a new building or an addition, so make sure to follow the instructions in Row 11 for each column. You are only required to enter information into the yellow cells in the table. The green cells in the table will populate when the relevant information is entered into the yellow cells. The orange cells in the worksheet (columns M and P) are the numbers that will be used to adjust the Total Energy Use for the year, and will automatically populate in Table 2 Progress (the worksheet on the next tab to the right). Starting with the current reporting year, enter any new buildings and building additions that occurred. Start with Building One, if you have more than one applicable building in a given year then move on to Building Two etc. Please change the generic "BUILDING ONE" label to the actual name of the building (e.g. Senior Center, High School, Police Station).
Building Stock Changes Calculator
Enter the name of the building in the appropriate cell, e.g. change "BUILDING ONE" to "High School". Name should match the name in MEI. | If NEW BUILDING, enter the OLD BUILDING'S sq. footage, if ADDITION, enter the building's sq. footage BEFORE the addition | If NEW BUILDING, enter the NEW BUILDING'S sq. footage, if ADDITION, enter the building's sq. footage AFTER the addition | THIS COLUMN WILL POPULATE % of energy to include | Non Weather-Normalized energy use (MMBTU) - this can be found in MassEnergyInsight - Energy Reduction Plan Guidance Table 3 (MMBtu) | If NEW BUILDING - enter the number 12. If ADDITION, enter the # of months the addition was online during the reporting yr.? | Non Weather-Normalized Prorated energy use (MMBTU) - | Weather-Normalized energy use (MMBTU) - This can be found in MassEnergyInsight - Annual Building Energy Use - Weather Normalized | Weather Normalized Prorated energy use (MMBTU) | Total Non-Weather Normalized Energy Use | Total Prorated Non-Weather Normalized Energy Use | Difference to be used to adjust Non-Weather-Normalized total - This will populate the apropriate cell in Table 2 - Progress | Total Weather-Normalized Energy Use | Total Prorated Weather-Normalized Energy Use | Difference to be used to adjust Weather-Normalized total This will populate the apropriate cell in Table 2 - Progress
2020
Police | 13920 | 36500 | 38.14% | 2850 | 12 | 1086.9041 | 3104.1 | 1183.8102 | 2850 | 1086.9041 |  | 3104.1 | 1183.8102
BUILDING TWO |  |  | 0% |  |  | 0 |  | 0
BUILDING THREE |  |  | 0% |  |  | 0 |  | 0
BUILDING FOUR |  |  | 0% |  |  | 0 |  | 0
BUILDING FIVE |  |  | 0% |  |  | 0 |  | 0 |  |  | -1763.0959 |  |  | -1920.2898
2019
Police | 13920 | 36500 | 38.14% | 3044 | 12 | 1160.8899 | 3064.5 | 1168.7079 | 3044 | 1160.8899 |  | 3064.5 | 1168.7079
BUILDING TWO |  |  | 0% |  |  | 0 |  | 0
BUILDING THREE |  |  | 0% |  |  | 0 |  | 0
BUILDING FOUR |  |  | 0% |  |  | 0 |  | 0
BUILDING FIVE |  |  | 0% |  |  | 0 |  | 0 |  |  | -1883.1101 |  |  | -1895.7921
2018
Police | 13920 | 36500 | 38.14% | 2902 | 12 | 1106.7353 | 2905.7 | 1108.1464 | 2902 | 1106.7353 |  | 2905.7 | 1108.1464
BUILDING TWO |  |  | 0% |  |  | 0 |  | 0
BUILDING THREE |  |  | 0% |  |  | 0 |  | 0
BUILDING FOUR |  |  | 0% |  |  | 0 |  | 0
BUILDING FIVE |  |  | 0% |  |  | 0 |  | 0 |  |  | -1795.2647 |  |  | -1797.5536

## Crit 3 - Table 2 Progress
Criterion 3 Step 2: Complete Table 2 - Progress
Table 2 Instructions: 1) Enter your community's baseline year (including whether it's a Fiscal Year or Calendar Year); 2) Enter total MMBtus per category (Rows 10-15) for the baseline year and the current reporting year. In MassEnergyInsight, this information is available in the "Annual Report Table 2" report; 3) If this is your community's first Annual Report, enter the energy consumption for past years as needed; 4) If your community did not submit an Annual Report last year, enter energy data for 2019 and 2020; 5) If your baseline includes a proportion of energy consumed by a regional school district, provide the pro-rated energy use in Row 18 for non weather-normalized use and Row 22 for weather-normalized use. Attach a worksheet (add a tab to this workbook) listing the buildings, their total energy use, and calculations on how you arrived at their prorated use; 6) If your community needs to pro-rate energy use due to building stock changes, use the calculator provided on the tab to the left and enter the resulting numbers in Row 17 for non weather-normalized data, and in Rows 21 for weather-normalized data.
WEATHER NORMALIZED DATA - DOER is requiring Green Communities to assess their progress using weather-normalized data through a DOER-approved weather normalization methodology. Qualifying methods include use of MassEnergyInsight or Energy Star Portfolio Manager. Please contact your Regional Coordinator for assistance if you use a different energy-tracking tool. Enter weather-normalized total energy consumption in Table 2, Row 20. In MassEnergyInsight, this information is available in the "Annual Report Table 2" report
Does the Community use Calendar Year (CY) or Fiscal Year (FY)? |  |  |  |  | FY
Table 2: Timeline of Annual Municipal Energy Use
| Baseline MMBtu | 2018 MMBtu | 2019 MMBtu | 2020 MMBtu | For Most Recent Year: Change vs. Baseline (%)
| 2015 | 2018 | 2019 | 2020
Null |  |  |  |  | Enter baseline year consumption in column D
Buildings | 51589 | 44098 | 44776 | 39481 | 23.47%
Open Space | 53 | 96 | 88 | 80 | -50.94%
Street & Traffic Lights | 390 | 389 | 389 | 341 | 12.56%
Vehicles | 7318 | 7662 | 6888 | 6979 | 4.632%
Water/Sewer | 7530 | 7626 | 7529 | 6979 | 7.317%
Building Stock Change Adjustment |  | -1795.2647 | -1883.1101 | -1763.0959
Regional School Prorated
TOTAL ENERGY CONSUMPTION (NO Weather Normalization) | 66880 | 58075.7353 | 57786.8899 | 52096.9041 | 22.1%
Weather Normalized Consumption (without building stock adjustment) | 63062 | 60682 | 61510 | 55731 | 11.63%
Building Stock Change Adjustment (weather - normalized) |  | -1797.5536 | -1895.7921 | -1920.2898
Regional School Prorated (weather-normalized)
TOTAL ENERGY CONSUMPTION (Weather-Normalized) | 63062 | 58884.4464 | 59614.2079 | 53810.7102 | 14.67%

## Crit 3 -Tbl 3 for Non-MEI Users
Criterion 3 Step 3: Complete Table 3 OR use MEI (NOTE: provide a separate table each for your baseline year and reporting year
Select Plan Year: | <Select Year>
NOTE: IF USING MASSENERGYINSIGHT, there is NO need to complete this table.
Table 3: Annual Municipal Energy Use in Native Units and MMBtu - Plan Year <Select Year>
Please enter "0" for any fuels not used
| Electricity |  | Natural Gas |  | #2 Distillate Fuel Oil |  | Propane |  | Gasoline |  | Diesel |  | Electric Renewable Energy |  | Thermal Renewable Energy |  | Total MMBtu
| kWh | MMBtu | Therms | MMBtu | Gallons | MMBtu | Gallons | MMBtu | Gallons | MMBtu | Gallons | MMBtu | kWh | MMBtu | Therms | MMBtu
School |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
Town Hall |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
Police Station |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
SUBTOTAL FOR BUILDINGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drinking Water/Wastewater Treatment Plant |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
Pumping in Aggregate |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
Open Space* |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
Vehicles in Aggregate |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
Street and Traffic Lights in Aggregate |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
TOTAL ENERGY CONSUMPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Crit 3 - ECMs
For use in next Table 4 - ECMs
Project Type | Definition/Includes:
Behav & Training | Behavioral programs, building operator training, etc.
Building Control | HVAC controls, energy management systems (NO vending misers)
Exterior Lighting | Streetlights, traffic lights, parking lots/garages, exterior lighting
Interior Lighting | Interior lighting & controls
Fuel Conversion | Conversion from one heating fuel type to another (often oil to natural gas)
Hot Water | Hot water heaters, pipe insulation, showerheads, faucet aerators, efficient dish washers
HVAC | Heating or cooling equipment, economizers, destratification fans, dehumidifiers, duct sealing or insulation (NO VFDs)
Pump/Motor/Drive | Pumps, motors, variable frequency/speed drives
Refrigeration | Refrigeration and controls, including vending misers
Retrocommission | Retrocommissioning and submetering projects
Vehicles | Energy-savings vehicles & their operations: GPS, anti-idling retrofits, routing software, big belly trash collectors, hybrid or EV purchases
Weatherization | Insulation, air-sealing, windows, etc.
Comprehensive | Large-scale retrofit of the entire building or multiple systems. Examples: building renovations, lighting + HVAC + EMS
Other | Use this only if types above do not fit
Status Type | Definition/Includes:
Complete | Project is complete & operational.
Active | Project is actively underway - procurement completed and in any stage of construction.
Planned | Identified project that will be pursued; may be in budgeting or procurement.
Abandoned | Project is not completed and will no longer be pursued.

## Crit 3 - Table 4 ECMs
Criterion 3 Step 4: Update Table 4 - ECMs
Update projects that were listed as "planned" or "active" in last Annual Report or Energy Reduction Plan and add new projects. Include all ECMs, not only ECMs funded by Green Communities grants.
| Click here to view a sample version of this table |  |  | Table 4 Energy Conservation Measures Data
ECMs - Update projects that were listed as "planned" or "active" in last Annual Report or Energy Reduction Plan and add new projects. |  |  |  | Status |  | Energy Data | [5 empty] | Financial Data |  |  |  |  | Reference Data
Category (select one from drop-down) | Building/Site Name | Energy Conservation Measure Name | ECM Type (select one from drop-down) | Status (select one from drop-down) | Status Date (Month -year completed or planned) | Projected Annual Electricity Savings (kWh) | Projected Annual Natural Gas Savings (therms) | Projected Annual Oil Savings (gallons) | Projected Annual Propane Savings (gallons) | Projected Annual Gasoline Savings (gallons) | Projected Annual Diesel Savings (gallons) | Projected Annual Cost Savings ($) | Total Installed Cost ($) | Green Community Grant ($) | Utility Incentives ($) | Net Cost ($) | Funding Source(s) for Net Costs | Source for Projected Savings
Buildings | Pfaff Recreation Center | Lighting | Exterior Lighting | Active | Winter 2020 | 12486 | [5 empty] | 2060 | 7050 |  | 7050 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Blake Middle School | Exterior LED | Exterior Lighting | Complete | 2018-05-08 | 67180 | [5 empty] | 11085 | 34133 | 18287 | 15846 | 0 | Green Communities Grant | Doer qurt report 1 may-jun 4th qut.docx
Buildings | Blake Middle School | All interior lighting (oringally only 200 Side Lighting) | Interior Lighting | Complete | 2019-11-22 | 107394 | [5 empty] | 17720 | 40700 |  | 40700 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Blake Middle School | 100-300 Side Lighting (consolidated with 200 Side lighting line item) | Interior Lighting | Complete | 2019-11-22 | [6 empty] | 0 | 0 |  | 0 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Blake Middle School | EMS | Retrocommission | Complete | Spring 2018 | 2008 | 2754 |  |  |  |  | 3521 | 25000 | 77956 | 3546 | 21454 | Green Communities Grant | Doer qurt report 1 may-jun 4th qut.docx
Buildings | Council on Aging | *COA parking Lights (presumed complete) | Exterior Lighting | Complete | Fall 2016 | 4508 | [5 empty] | 676 | 3000 |  | 1127 | 1873 | Town Budget | Town of Medfield
Buildings | Council on Aging | *Interior Lighting (presumed complete) | Interior Lighting | Complete | Fall 2016 | 16750 | [5 empty] | 2512 | 34570 |  | 4187 | 30383 | Town Budget | AECOM (Appendix B1)
Buildings | Dale Street Elementary School | All interior lighting (oringally only First Floor Lighting) | Interior Lighting | Complete | 2019-11-22 | 57416 | [5 empty] | 9474 | 21688 |  | 21688 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Dale Street Elementary School | 2nd Floor Lighting (combined with 1st floor lighting line item) | Interior Lighting | Complete | 2019-11-22 | [6 empty] | 0 | 0 |  | 0 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Medfield High School | Exterior LED | Exterior Lighting | Complete | 2018-05-08 | 93868 | [5 empty] | 15488 | 46628 | 24484 | 22144 | 0 | Green Communities Grant | Doer qurt report 1 may-jun 4th qut.docx
Buildings | Medfield High School | All interior lighting (oringally only First Floor Lighting) | Interior Lighting | Complete | 2019-11-22 | 242014 | [5 empty] | 39932 | 88334 |  | 88334 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Medfield High School | 2nd Flr & LL Lighting (consolidate with 1st floor lighting line item) | Interior Lighting | Complete | 2019-11-22 | [6 empty] | 0 | 0 |  | 0 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Medfield Public Library | MPL Exterior Lighting | Exterior Lighting | Complete | 2018-05-08 | 5510 | [5 empty] | 827 | 9287 | 1173 | 5886 | 2229 | Green Communities Grant | Doer qurt report 1 may-jun 4th qut.docx
Buildings | Medfield Public Library | *MPL Lighting (presumed complete) | Interior Lighting | Complete | Summer 2020 | 16305 | [5 empty] | 2446 | 350 |  |  | 350 | Town Budget | Town of Medfield (Appendix C1)
Buildings | Memorial Elementary School | Exterior LED | Exterior Lighting | Complete | 2018-05-08 | 53134 | [5 empty] | 8767 | 29210 | 16620 | 12590 | 0 | Green Communities Grant | Doer qurt report 1 may-jun 4th qut.docx
Buildings | Memorial Elementary School | All interior lighting (oringally only Wings 1 & 2 Lighting) | Interior Lighting | Complete | 2019-11-22 | 70937 | [5 empty] | 11705 | 28100 |  | 28100 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Memorial Elementary School | Wing 3 Lighting (consolidated with Wing 1/2 line item) | Interior Lighting | Complete | 2019-11-22 | [6 empty] | 0 | 0 |  | 0 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Street & Traffic Lights | Streetlights | Exterior LED | Exterior Lighting | Complete | 2019-06-01 | 69435 | [5 empty] | 31870 | 81505 |  | 11182 | 70323 | Green Communities Grant | Fred Davis Corporation (Appendix E1)/ Project Estimate 032217
Buildings | Town Garage | *Garage Controls (presumed complete) | Building Control | Complete | Fall 2016 |  | 33200 |  |  |  |  | 29880 | 0 |  | 0 | 0 | Town Budget | Town of Medfield
Buildings | Town Hall | TH Parking Lights | Exterior Lighting | Complete | 2018-05-08 | 15972 | [5 empty] | 1916 | 3812 | 1677 | 2135 | 0 | Green Communities Grant | Doer qurt report 1 may-jun 4th qut.docx
Buildings | Town Hall | Interior Lighting | Interior Lighting | Complete | Spring 2020 | 31869 | [5 empty] | 5258 | 15000 |  | 15000 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Wheelock Elementary School | Exterior LED | Exterior Lighting | Complete | 2018-05-08 | 5366 | [5 empty] | 885 | 7445 | 6041 | 1404 | 0 | Green Communities Grant | Doer qurt report 1 may-jun 4th qut.docx
Buildings | Wheelock Elementary School | All interior lighting (oringally only First Floor Lighting) | Interior Lighting | Complete | 2019-11-22 | 65074 | [5 empty] | 10737 | 63000 |  | 63000 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Wheelock Elementary School | 2nd Floor Lighting (combined with 1st floor lighting line item) | Interior Lighting | Complete | 2019-11-22 | [6 empty] | 0 | 0 |  | 0 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Wheelock Elementary School | New Boilers (2) | HVAC | Complete | Summer 2016 |  | 4836 |  |  |  |  | 4352 | End-of-life replacement |  | School Building Authority Grant | End-of-life replacement | Town Budget | Town of Medfield
Buildings | Town Garage | Interior Lighting | Interior Lighting | Complete | Spring 2020 | 49788 | [5 empty] | 8215 | 22500 |  | 22500 | 0 | No cost to Town of Medfield | Commonwealth Electrical Technologies
Buildings | Medfield Public Library | Interior Lighting | Interior Lighting | Comptete | Spring 2020 | 41298 | [5 empty] | 6195 | 90695 |  | 10325 | 80370 | Green Communities Grant | AECOM (Appendix B2)
Buildings | Blake Middle School | Behavioral Based Measures | Behavioral and Training | Planned | Fall 2021 | 32757 | [5 empty] | 3931 | 1000 |  | Pay-for-Performance | 1000 | Green Communities Grant | MAPC (Appendix D1)
Buildings | Blake Middle School | Roof Top Units Repair | HVAC | Planned | FY2021 | [7 empty] | 40,00
Buildings | Blake Middle School | Replace Shut Off Valves | Hot Water | Planned | FY2021 | [7 empty] | 20000
Buildings | Blake Middle School | Replace HW heater | HVAC | Planned | FY2022 | [7 empty] | 200000
Buildings | Blake Middle School | Replace Shut Off Valves | Hot Water | Planned | FY2022 | [7 empty] | 15000
Buildings | Blake Middle School | Gym HVAC/Fan Coil Unit Replace,ent | HVAC | Planned | FY2022 | [7 empty] | 40000
Buildings | Blake Middle School | Replace windows at curtain wall café | Weatherization | Planned | FY2022 | [7 empty] | 30000
Buildings | Blake Middle School | Replace sealants at Windows/Doors | Weatherization | Planned | FY2024 | [7 empty] | 200000
Buildings | Blake Middle School | Brick Façade Repair Engineering | Weatherization | Planned | FY2024 | [7 empty] | 40000
Buildings | Blake Middle School | brick façade repair | Weatherization | Planned | FY2025 | [7 empty] | 300000
Buildings | Blake Middle School | Roof Insulation | Weatherization | Planned | Summer 2020 | 1111 | 6212 |  |  |  |  | 7144 | 100000 |  | 50000 | 50000 | Green Communities Grant | Rise Engineering (Appendix A2)
Buildings | Blake Middle School | New DHW Storage | Hot Water | Planned | Summer 2022 |  | 1050 |  |  |  |  | 1202 | 8000 |  | 4000 | 4000 | Green Communities Grant | Rise Engineering (Appendix A1)
Buildings | Blake Middle School | Low-Flow Aerators and Showerheads, Spray Valve | Hot Water | Planned | Winter 2021 |  | 719 |  |  |  |  | 827 | 720 |  | 720 | 0 | N/A | Rise Engineering (Appendix A1)
Buildings | Council on Aging | Building Envelope Repair | Weatherization | Planned | FY2024 | [7 empty] | 12000
Buildings | Council on Aging | COA Entrance | Weatherization | Planned | Winter 2020 |  | 500 |  |  |  |  | 450 | 5500 |  |  | 5500 | Town Budget | Town of Medfield
Buildings | Dale Street Elementary School | Replace Tempering Valves | Hot Water | Planned | FY2021 | [7 empty] | 12000
Buildings | Dale Street Elementary School | Replace Shut Off Valves | Hot Water | Planned | Fy2024 | [7 empty] | 20000
Buildings | Dale Street Elementary School | Exterior LED | Exterior Lighting | Planned | Winter 2020 | 2037 | [5 empty] | 336 | 927 |  | 509 | 418 | Green Communities Grant | Rise Engineering (Appendix A3)
Buildings | Dale Street Elementary School | Steam traps | HVAC | Planned | Winter 2020 |  | 7710 |  |  |  |  | 8866 | 25000 |  | 12500 | 12500 | Green Communities Grant | Rise Engineering
Buildings | Dale Street Elementary School | Low-Flow Aerators and Spray Valve | Hot Water | Planned | Winter 2021 |  | 522 |  |  |  |  | 600 | 414 |  | 414 | 0 | N/A | Rise Engineering (Appendix A4)
Buildings | High School | Lighting control | Interior Lighting | Planned | FY2021 | [7 empty] | 15000
Buildings | High School | Air Handling Units (replace/repair) | HVAC | Planned | FY2022 | [7 empty] | 10000
Buildings | High School | Exterior door replacement | Weatherization | Planned | FY2022 | [7 empty] | 10
Buildings | High School | Rooftop Units (RTU) Repair | HVAC | Planned | FY2022 | [7 empty] | 20000
Buildings | High School | Replace Shut Off Valves | Hot Water | Planned | FY2022 | [7 empty] | 10000
Buildings | High School | Replace Shower Head | Hot Water | Planned | FY2022 | [7 empty] | 8000
Buildings | High School | Window repair | Weatherization | Planned | FY2023 | [7 empty] | 40000
Buildings | High School | Brick Façade Repair | Weatherization | Planned | FY2023 | [7 empty] | 50000
Buildings | High School | Envelope sealant replacement | Weatherization | Planned | FY2023 | [7 empty] | 303000
Buildings | High School | window weatherstripping | Weatherization | Planned | FY2024 | [7 empty] | 20000
Buildings | High School | Window sealant replacement | Weatherization | Planned | FY2025 | [7 empty] | 200000
Buildings | High School | boiler replacement | HVAC | Planned | FY2025 | [7 empty] | 100000
Buildings | Library | Brick Façade Engineering/Repair | Weatherization | Planned | FY2022 | [7 empty] | 70000
Buildings | Library | EPDM Roof Engineering/Repair | Weatherization | Planned | FY2022 | [7 empty] | 60000
Buildings | Library | Exterior Sealant Repair | Weatherization | Planned | FY2023 | [7 empty] | 20000
Buildings | Library | ATC Controls Upgrade | Building Control | Planned | FY2024 | [7 empty] | 10000
Buildings | Medfield High School | EMS | Retrocommission | Planned | Fall 2020 | 13917 | 2959 |  |  |  |  | 5908 | 50000 |  | 5221 | 44779 | Green Communities Grant | Rise Engineering (Appendix A4)
Buildings | Medfield High School | Behavioral Based Measures | Behavioral and Training | Planned | Fall 2021 | 72649 | [5 empty] | 8718 | 1000 |  | Pay-for-Performance | 1000 | Green Communities Grant | MAPC (Appendix D1)
Buildings | Medfield High School | Low-Flow Aerators and Showerheads, Spray Valve | Hot Water | Planned | Winter 2021 |  | 1052 |  |  |  |  | 1209 | 1114 |  | 1114 | 0 | N/A | Rise Engineering (Appendix A4)
Buildings | Medfield Public Library | EMS | Building Controls Installation | Planned | Summer 2024 | 2605 | 213 |  |  |  |  | 685 | 50000 |  | 9600 | 40400 | Green Communities Grant | Rise Engineering (Appendix A4)
Buildings | Medfield Public Library | Attic Air Sealing | Weatherization | Planned | Winter 2020 | 521 | 381 |  |  |  |  | 380 | 3500 |  | 1750 | 1750 | Town Budget | Rise Engineering (Appendix A7)
Buildings | Medfield Public Library | Attic Insulation | Weatherization | Planned | Winter 2020 | 73 | 86 |  |  |  |  | 86 | 2500 |  | 0 | 2500 | Green Communities Grant | Rise Engineering (Appendix A7)
Buildings | Medfield Public Library | Low-Flow Aerators | Hot Water | Planned | Winter 2021 | 3984 | [5 empty] | 637 | 88 |  | 0 | 88 | Green Communities Grant | Rise Engineering (Appendix A4)
Buildings | Medfield Public Library | Pipe Insulation | HVAC | Planned | Winter 2021 |  | 46 |  |  |  |  | 46 | 600 |  |  | 600 | Green Communities Grant | Rise Engineering (Appendix A7)
Buildings | Memorial Elementary School | Exterior Lighting Control System | Exterior Lighting | Planned | FY2021 | [7 empty] | 15000
Buildings | Memorial Elementary School | Replace Split Systems |  | Planned | FY2022 | [7 empty] | 45000
Buildings | Memorial Elementary School | Johnson Controls BMS Upgrade | Building Control | Planned | FY2022 | [7 empty] | 10000
Buildings | Memorial Elementary School | Roof Top Units Repair | HVAC | Planned | FY2022 | [7 empty] | 10000
Buildings | Memorial Elementary School | Replace HW Heater and Shut Off Valves | HVAC | Planned | FY2022 | [7 empty] | 120000
Buildings | Memorial Elementary School | Roof Top Units Repair | HVAC | Planned | FY2022 | [7 empty] | 10000
Buildings | Memorial Elementary School | Low-Flow Aerators and Spray Valve | Hot Water | Planned | Winter 2021 |  | 539 |  |  |  |  | 620 | 425 |  | 425 | 0 | N/A | Rise Engineering (Appendix A4)
Buildings | Memorial Elementary School | EMS | System Upgrade and Retrocommissioning | Planned | Winter 2022 | 6127 | 1520 |  |  |  |  | 2850 | 100000 |  | 9759 | 90241 | Green Communities Grant | Rise Engineering (Appendix A4)
Buildings | Town Hall | EMS | Retrocommission | Planned | Fall 2024 | 3212 | 212 |  |  |  |  | 758 | 15000 |  | 640 | 14360 | Green Communities Grant | Rise Engineering (Appendix A4)
Buildings | Town Hall | Exterior Envelope Façade Repairs | Weatherization | Planned | FY2021 | [7 empty] | 120000
Buildings | Town Hall | Roof repairs | Weatherization | Planned | FY2021 | [7 empty] | 20000
Buildings | Town Hall | fan coil units (repair/replace) | HVAC | Planned | FY2022 | [7 empty] | 9000
Buildings | town hall | AHU (Air Handling Unity) repairs | HVAC | Planned | FY2022 | [7 empty] | 2000
Buildings | town hall | HW heater replacement | Hot Water | Planned | FY2023 | [7 empty] | 8000
Buildings | town hall | Chillder Plant Recommissioning | HVAC | Planned | FY2024 | [7 empty] | 10000
Buildings | town hall | Exhaust Fan Repair | HVAC | Planned | FY2024 | [7 empty] | 5000
Buildings | town hall | Exterior Envelope Sealant Replacement | Weatherization | Planned | FY2025 | [7 empty] | 40000
Buildings | Town Hall | Low-Flow Aerators | Hot Water | Planned | Winter 2020 | 5976 | [5 empty] | 956 | 132 |  | 0 | 132 | Green Communities Grant | Rise Engineering (Appendix A4)
Vehicles | Vehicles | Anti-Idling Policy | Vehicles | Planned | Fall 2024 |  |  |  |  | 1000 | 1000 | 3500 |  |  |  | 0 | N/A | Town of Medfield
Vehicles | Vehicles | Fleet Management Strategies | Vehicles | Planned | Summer 2021 |  |  |  |  | 2380 | 3140 | TBD | TBD |  | 0 | TBD | Green Communities Grant | MAPC (Appendix D2)
Buildings | Wheelock Elementary School | Replace Tempering Valves | Hot Water | Planned | FY2021 | [7 empty] | 110000
Buildings | Wheelock Elementary School | fan coil units (repair/replace) | Hvac | Planned | fy2021 | [7 empty] | 70000
Buildings | Wheelock Elementary School | Replace Shut Off Valves | Hot Water | Planned | FY2021 | [7 empty] | 50000
Buildings | Wheelock Elementary School | Exhaust Fan Replacement | HVAC | Planned | FY2021 | [7 empty] | 25000
Buildings | Wheelock Elementary School | electrical upgrades | Other | Planned | Fy2022 | [7 empty] | 40000
Buildings | Wheelock Elementary School | replace values to FanCoils Units | hvac | Planned | FY2023 | [7 empty] | 30000
Buildings | Wheelock Elementary School | replace pneumatic temp controls | Building Control | Planned | FY2025 | [7 empty] | 100000
Buildings | Wheelock Elementary School | Low-Flow Aerators and Spray Valve | Hot Water | Planned | Winter 2021 |  | 454 |  |  |  |  | 522 | 370 |  | 370 | 0 | N/A | Rise Engineering (Appendix A4)
To insert additional rows, select this row, right-click, and select "Insert." | To insert additional rows, select this row, right-click, and select "Insert."
[5 empty] | TOTAL Projected Savings | 1173281 | 64965 | 0 | 0 | 3380 | 4140 | 275752 | 3692307 | 146238 | 473766 | 476250
| TOTAL MMBtu SAVINGS |  |  | 11494.3148 |  | 4003.2348 | 6496.5 | 0 | 0 | 419.12 | 575.46

## Crit 3 - Tbl 4 ECMs SAMPLE Data
SAMPLE Criterion 3 Step 4: Complete Table 4 - ECMs
Click here to return to Table 4 |  |  |  | Table 4 SAMPLE Energy Conservation Measures Data
ECMs |  |  |  | Status |  | Energy Data | [5 empty] | Financial Data |  |  |  |  | Reference Data
Category | Building/Site Name | Energy Conservation Measure Name | ECM Type (select one from drop-down) | Status (select one from drop-down) | Status Date (Month -year completed or planned) | Projected Annual Electricity Savings (kWh) | Projected Annual Natural Gas Savings (therms) | Projected Annual Oil Savings (gallons) | Projected Annual Propane Savings (gallons) | Projected Annual Gasoline Savings (gallons) | Projected Annual Diesel Savings (gallons) | Projected Annual Cost Savings ($) | Total Installed Cost ($) | Green Community Grant ($) | Utility Incentives ($) | Net Cost ($) | Funding Source(s) for Net Costs | Source for Projected Savings
Buildings | Green School | Lighting Retrofit | Interior Lighting | Complete | 2020-02-01 | 95252 | 0 | 0 | 0 | 0 | 0 | 8000 | 25000 | 0 | 12500 | 12500 | Town Capital Plan FY2011 | http://www.energystar.gov/ia/business/downloads/BP_Checklist.pdf
Buildings | Town Hall | Air Sealing | Weatherization | Active | 2020-12-01 | 0 | 230 | 0 | 0 | 0 | 0 | 1100 | 3500 | 1750 | 1750 | 0 | N/A | A-Z Energy Audit, 2008
Buildings | Town Hall | New Boiler | HVAC | Planned | 2022-11-01 | 0 | 17122 | 0 | 0 | 0 | 0 | 5000 | 50000 | 35000 | 15000 | 0 | N/A | Boilers-to-Go Quote, 2009
Street Lights |  | LED Conversion | Exterior Lighting | Active | 2021-01-01 | 6000 | 0 | 0 | 0 | 0 | 0 | 2500 | 5000 | 0 | 2500 | 2500 | Town Operating Budget FY2011 | LED Signals Today Quote, 2009
Buildings | Drinking Water Treatment Plant | 2 Variable Speed Drives | Pump/Motor/Drive | Complete | 2020-03-01 | 500000 | 0 | 0 | 0 | 0 | 0 | 40000 | 200000 | 0 | 100000 | 100000 | Town Bond FY2016 | Energy Masters Technical Study, 2010
Vehicles |  | Anti-idling retrofit for 2 police cruisers | Vehicles | Planned | 2020-08-01 | 0 | 0 | 400 | 400 | 400 | 400 | 4500 | 6000 | 0 | 0 | 6000 | Town Operating Budget FY2018 | green.autoblog.com
TOTAL Projected Savings | [5 empty] | 601252 | 17352 | 400 | 400 | 400 | 400 | 61100 | 289500 | 36750 | 131750 | 121000
TOTAL MMBtu SAVINGS |  |  |  | 4661.7998 |  | 2051.4718 | 2411.928 | 49.6 | 49.6 | 49.6 | 49.6

## RE Guidance
GUIDANCE FOR REPORTING RENEWABLE ENERGY GENERATION AS ENERGY CONSUMPTION
The following scenarios apply to renewable energy systems that are interconnected to the electric grid. It is possible that more than one scenario applies to the same renewable energy system; for example, a solar PV system may generate less energy than its building uses in the winter (scenario 1), but generate more energy than its building uses in the summer (scenario 2). Ideally, calculations should be done for each month.
1) Do you have Conventional Net Metering?
If yes, see RE Scenario 1 and RE Scenario 2
2) Do you have Virtual Net Metering?
If yes, see RE Scenario 3
3) Do you live in an MLP?
If yes, see RE Scenario 4
RE Scenario 1: Conventional Net Metering, System Generation < Building Use = Importing Power
If the building uses more electricity than the RE system generates, your electric meter registers postitive. The building is importing power from the electric company. Then a Green Community should add in the amount of RE generation. This means the total building energy use = total kWh on electric bill + kWh generated by RE.
For example:
Total Grid Electricity on electric bill (kWh): 3,000
Total Net Metering Credits on electric bill (kWh): 0
Total generated by the RE system (kWh): +7,000
Total building use (kWh): 10,000
Find and Calculate: Find the kWh generated each month from your RE system. Contact your Regional Coordinator if you are having trouble finding the kWh generated each month.
Action: Load the building renewable energy usage into MassEnergyInsight. Create a separate account for each RE system at each building. Load the RE generation for each month by going to “Upload a Spreadsheet.” Choose “solar electric” or “wind power.” Upload your usage data. If not using MassEnergyInsight, report to DOER in your Annual Report .
RE Scenario 2: Conventional Net Metering, System Generation > Building Use = Exporting Power
If the RE system generates more electricity than the building uses your electric meter registers negative. The RE system is exporting power to the electric company. Then a Green Community should not add in the amount of generation over and above what the building used. This means the total building energy use = kWh generated by RE – kWh credited to electric bill for net metering.
** Contact your Regional Coordinator if you have negative use on your electric bill **
For example:
Total Grid Electricity on electric bill (kWh): 0
Total Net Metering Credits on electric bill (kWh): -1,000
Total generated by the RE system (kWh): +7,000
Total building use (kWh): 6,000
For help locating net metering credits on your electric bill go to:
https://www.nationalgridus.com/non_html/MA_DG_First_Bill.pdf
https://www.eversource.com/Content/ema-e/residential/programs-services/interconnections-net-metering/net-metering-faq
Find and Calculate: Find the total kWh generated each month from your RE system. Find the net metering credits in kWh applied to your electric bill each month. Subtract the net metering credits in kWh from the total RE generated. This is your building’s NET use of renewable energy generated. Contact your Regional Coordinator if you are having trouble finding the KWh generated and credited each month.
Action: Load the NET building renewable energy usage into MassEnergyInsight. Create a separate account for each RE system for each building. Load the RE generation for each month by going to “Upload a Spreadsheet.” Choose “solar electric” or “wind power.” Upload your usage data. Or, report to DOER in your Annual Report.
RE Scenario 3: Virtual Net Metering
If a building is virtually net metered, in which the RE system has its own separate meter but the financial credits are applied to a different building, then the actual amount of electricity use of the building will be on its electric bill. For example, a municipality may have built a solar PV array on a closed landfill. The PV system has a meter but does not link to any buildings that consume a substantial amount of energy. (The PV system will be linked to its inverter and perhaps to a small shed or security lights.) The financial value of the electricity that is generated by the landfill solar PV system is applied to an account for electric use at the town hall and to an account for electric use at the library. The electric bills for the town hall and library thus will show the amount of electricity that is actually used by those buildings, but only charge for the amount of electricity above and beyond what was generated by the solar PV system on the landfill. See DOER’s Net Metering page for more details on credits for renewable generation.
Information Needed: Written confirmation of virtual net metering documenting there is a separate meter used for the RE system with only a small load-side usage. The load-side usage should be reported to MassEnergyInsight under Scenario 2 above.
Action: Generation does not impact baseline and should NOT be loaded into MassEnergyInsight. Provide information needed as noted above. Report load-side usage under Scenario 2 above.
RE Scenario 4: RE Generation to Control Rates (for MLPs)
If an MLP uses its RE generation to control its system-wide rates and does not use the RE for a specific municipal building, either directly or through virtual net metering, then the amount of RE generation does not need to be included.
Information Needed: Written confirmation of RE generation for system-wide benefit with no virtual net metering. The load-side usage should be reported to MassEnergyInsight under Scenario 2 above.
Action: Generation does not impact baseline and should NOT be loaded into MassEnergyInsight. Provide information needed as noted above.

## Crit 3 - Table 5 RE
Please refer to Guidance on Reporting Renewable Energy Generation and Only Include Projects with Conventional
Net Metering (scenario 1 and scenario 2) in Table 5
Criterion 3 Step 5: Complete Table 5 - Renewable Energy
Project Description |  |  |  | Status and Timing |  | Electricity Data |  | Thermal Energy Data (representing consumption) |  |  | Financial Data |  |  |  |  | Reference Info
Project Name | Resource Type (select from drop down) | Site Type (select from drop down) | Town Procuring Energy Output? (select from drop down) | Project Status (select from drop down) | Year Completed (i.e., 2016) | Size of System (kW, DC) | Annual Electricity Generation (kWh) | Annual Natural Gas (therms) | Annual Wood (cords) | Annual Wood (pellets) | Annual Cost Savings ($) | Total Installed Cost ($) | Green Community Grant ($) | Other Grant ($) | Net Cost ($) | Funding Source(s) for Net Costs | Source for Projected Savings
Sample Data - City Hall | Solar PV, Roof | Municipal Building | Y - conventional net metered | Complete | 2016 | 26.5 | 26507 |  |  |  | 302.4 | 439632 | 0 | 337500 | 102132 | City Capital Funds | Soltrex online PV systems portfolio dashboard
WasterWater Treatment Plan | Solar PV, Ground | Water/Wastewater Plant | Y - conventional net metered | Complete | 2015 | 281 | 29956 |  |  |  |  | 431800 | 0 | 180000 | 251800 | Town Bond
Police (Public Safety Building) | Solar PV, Roof | Municipal Building | Y - conventional net metered | Complete | 2016 | 60 | 6871 | [5 empty] | 0
To insert additional rows, select this row, right-click, and select "Insert."
TOTALS | [6 empty] | 36827 | 0 | 0 | 0
TOTAL RENEWABLE ENERGY PRODUCTION (MMBtu) | [6 empty] | 125.6537 |  | 0 | 0 | 0 | 431800 | 0 | 180000 | 251800

## Crit 4 - Vehicle Policies
Criterion 4 - Purchase Fuel Efficient Vehicles
Since your last Annual Report OR Green Communities Designation (if first Annual Report) has your municipality…
1) Replaced an exempt or non-exempt vehicle? | NO
2) Acquired a new exempt or non-exempt vehicle, and/or conducted inter-departmental vehicle transfers? | NO
NOTE: Inter-departmental transfers must comply with MPG requirements of Fuel Efficiency Policy
If the answer to #1 and/or #2 above is "yes", Please provde a list of all vehicles (Both exempt and non-exempt) for ALL departments, including schools (as appropriate), that were acquired, retired and/or transferred in since your last Annual Report or Designation Application (if first Annual Report). Please do not report any exempt off-road vehicles, trailers, etc. In the spreadsheet on the following tab (Crit 4 -Table 6), 1) List in the top table all vehicles acquired or transferred since the last annual report, noting which vehicles they are replacing, and/or 2) List all vehicles removed from the municipal fleet in the bottom table
3) Installed an electric vehicle charging station during the reporting period? | NO
4) Installed idle-reduction technology on any vehicles during the reporting period? | NO
5) Implemented anti-idling technology and/or campaigns during the reporting period? | YES
6) Implemented a driving monitoring system that records miles driven and/or fuel consumption during the reporting period? | NO
7) Implement a fuel use reporting system for operators on fuel efficiency during the reporting period? | NO
8) Implement any other policies and/or technologies not listed above during the reporting period? | NO
Estimate annual fuel savings from each new technology or policy in the yellow box below. Also attach any new vehicle policies and technologies adopted by the municipality to this annual report.
9) Does the community meet Criterion 4 through alternative compliance? | NO

## Crit 4- Table 6 Vehicle Inv
Changes in Vehicle Inventory
Provide a list of all vehicles (both exempt and non-exempt) for ALL departments, including schools, that were acquired, retired, and/or transferred to other departments since your last Annual Report or Designation Application (if this is your community's first Annual Report). Please do not report any exempt off-road vehicles, trailers, streetsweepers, etc. NOTE: For the purposes of the program, municipalities must use the EPA combined fuel economy estimate listed at FuelEconomy.gov for vehicles with a GVWR < 8,500 pounds. If the vehicle is not listed on FuelEconomy.gov then list N/A for MPG rating.
List new acquisitions in this table
Is this a new acquisition? | If the vehicle is a replacement, what vehicle did it replace? Please reference vehicle listed in "Vehicles Retired" table below. If transferred from another department, indicate which one. | Make | Model | Market Class (choose from drop-down list) | Model Year | Month/Year acquired | Drive System (choose from drop-down list) | > 8500 pounds? (choose from drop-down list) | COMBINED MPG Rating (Click here for fueleconomy.gov) | Vehicle Function (i.e. DPW, Police, Inspector) | Used for Emergency Response? (choose from drop-down list) | ADMIN ONLY
[12 empty] | Exempt or Non-Exempt? | Meets GC Fuel Efficiency Rating?
None to report
List vehicle retirements in this table
| Was this vehicle removed from the fleet? | Make | Model | Market Class | Model Year | Month/Year Purchased | Drive System: 2WD, 4WD, AWD | > 8500 pounds? (Y or N or NA) |  | Vehicle Function before retirement (i.e. DPW, Police, Fire) | Used for Emergency Response? (choose from drop-down list) | ADMIN ONY Exempt or Non-Exempt?
| YES | Ford | F250 | Pickup Truck | 2001 | unknown | 4WD | Y |  | Water Department | N | Exempt
| YES | Mack | Pumper | Other | 1983 | unknown | 2WD | Y |  | Fire Department | Y | Exempt

## Crit 4- Table 6 SAMPLE
Changes in Vehicle Inventory
Provide a list of all vehicles (both exempt and non-exempt) for ALL departments, including schools, that were acquired, retired, and/or transferred to other departments since your last Annual Report or Designation Application (if this is your community's first Annual Report). Please do not report any exempt off-road vehicles, trailers, streetsweepers, etc. NOTE: For the purposes of the program, municipalities must use the EPA combined fuel economy estimate listed at FuelEconomy.gov for vehicles with a GVWR < 8,500 pounds. If the vehicle is not listed on FuelEconomy.gov then list N/A for MPG rating.
List new acquisitions in this table
Is this a new acquisition? | If the vehicle was transferred, what vehicle did it replace? Please reference vehicle listed in "Vehicles Retired" table below. If transferred from another department, indicate which one. | Make | Model | Market Class (choose from drop-down list) | Model Year | Month/Year acquired | Drive System (choose from drop-down list) | > 8500 pounds? (choose from drop-down list) | COMBINED MPG Rating (Click here for fueleconomy.gov) | Vehicle Function (i.e. DPW, Police, Inspector) | Used for Emergency Response? (choose from drop-down list) | ADMIN ONLY
[12 empty] | Exempt or Non-Exempt? | Meets GC Fuel Efficiency Rating?
YES | Crown Victoria in row 42 | Ford | Focus | Car | 2018 | 2017-08-01 | 2WD | N | 31 | Inspector/Assessor shared car | N | Non-Exempt | Yes
YES | New Vehicle; no replacement | Ford | Explorer | Sport Utility Vehicle or SUV | 2017 | 2018-04-01 | AWD | N | 19 | Police CRUISER | Y | Exempt | N/A, Vehicle is exempt
YES | Taurus in row 43 | Ford | Explorer | Sport Utility Vehicle or SUV | 2018 | 2018-04-02 | AWD | N | 19 | Police CRUISER | Y | Exempt | N/A, Vehicle is exempt
YES | chevy dump row 44 | Ford | F550 | Pickup Truck | 2018 | 2018-04-01 | 4WD | Y | N/A | DPW | N | Exempt | N/A, Vehicle is exempt
Transferred | Transferred from Engineer Dept. | Cheverlet | Silverado | Pickup Truck | 2014 | 2014-07-01 | 4WD | N | 18 | Parks and Recreation | N | Non-Exempt | Yes
YES | Chevy Silverado (above) | Cheverlet | Equinox | Sport Utility Vehicle or SUV | 2018 | 2018-07-01 | AWD | N | 20 | Engineer | N | Non-Exempt | Yes
List vehicle retirements in this table
| Was this vehicle removed from the fleet? | Make | Model | Market Class | Model Year | Month/Year Purchased | Drive System: 2WD, 4WD, AWD | > 8500 pounds? (Y or N or NA) |  | Vehicle Function before retirement (i.e. DPW, Police, Fire) | Used for Emergency Response? (choose from drop-down list) | ADMIN ONY Exempt or Non-Exempt?
| YES | Ford | Crown Victoria | Car | 1999 | 1999-07-01 | 2WD | N |  | Assesor | Y | Exempt
| YES | Ford | Taurus | Car | 2005 | 2005-01-01 | 2WD | N |  | police cruiser | N | Non-Exempt
| YES | Chevy | dump | Pickup Truck | 2006 |  |  | Y |  | DPW | N | Exempt

## Crit 5 - Stretch Code complianc
Criterion 5 - Minimize Life-Cycle Costs in New Construction
Is the stretch code still in effect? | YES
Were any residential occupancy permits issued since your last Annual Report or Designation Application (if first Annual Report)? | YES
How many occupancy permits were issued for new commericial construction over 100,000 sq.ft.? | 0
Please provide in the space below any anecdotal information about your community's experience with the Stretch Code (e.g. local banks loaning more to people purchasing stretch code homes, satisfied homeowners, frustrated builders, etc.).
Stretch code is still in effect. Occupancy permits were given to 17 residential buildings and an apartment building with 16 units.
DOER will access HERS scores reported to ResNet to ensure compliance

## Other Notes
Other Notes
Please provide in the space below any information about additional measures taken by the community that are consistent with its status as a designated Green Community(e.g. additional as-of-right siting put in place since designation for renewable or alternative energy generation, R&D, or Manufacturing facilities).
Please provide in the space below what percentage of your municipality's electricity consumption is supported by renewable energy generation? Of this percentage, how much of this is onsite generation? How much of this is net metering? How much of this is through the purchase of Renewable Energy Certificates (RECs)?
Medfield has a total of 125 MMBTus of solar energy on-site which makes up .3% of total building energy usage.

## DOER reference (hidden)
<Select One> | 3 | blank | blank | blank | <Select YES or NO> | <Select Year> | <Select Drive System> | <Select One> | <Select One> | <Select One> | <Select One> | <Select One> | <Select One> | <Select NR or C> | <Select One> |  | Crit 4 - Vehicle Inventory
Buildings | 2010-05-01 | R&D | 43D | Yes per designation ap | YES | FY2018 | 2WD | Y | E | NR | Behav & Training | Null | Complete | NR | 1 |  | Market Class List | Used for Emergency Response?
Open Space | 2010-12-01 | MFR | Local | Yes per AR 2011 | NO | FY2019 | 4WD | N | NE | RR | Building Control | Buildings | Active | C | 2 |  | <Select One> | <Select One>
Street & Traffic Lights | 2011-07-01 | R&D and MFR |  | No per designation app | Transferred | FY2020 | AWD | NA |  | C | Exterior Lighting | Open Space | Planned |  | 3 |  | Car | Y | Car2WD | 29
Vehicles | 2011-12-01 | R&D & MFR & Solar |  |  |  | CY2016 |  |  |  |  | Interior Lighting | Street & Traffic Lights | Abandoned |  | 4 |  | Minivan or Van | N | Car4WD | 24
Water/Sewer | 2012-07-01 | Generation; Solar |  |  |  | CY2017 |  |  |  |  | Fuel Conversion | Vehicles |  |  | 5 |  | Pickup Truck |  | CarAWD | 24
| 2012-12-01 | Generation; Wind |  |  |  | CY2018 |  |  |  |  | Hot Water | Water/Sewer |  |  | 6 |  | Sport Utility Vehicle or SUV |  | Minivan or Van2WD | 20
| 2013-12-01 | Generation; Solar & Wind |  |  |  | CY2019 |  |  |  |  | HVAC |  |  |  | 7 |  | Other |  | Minivan or Van4WD | 18
| 2014-12-01 | [9 empty] | Pump/Motor/Drive |  |  |  | 8 |  |  |  | Minivan or VanAWD | 18
| 2015-12-01 |  |  | <Select one> | [6 empty] | Refrigeration |  |  |  | 9 |  |  |  | Pickup Truck2WD | 17
| 2017-02-01 |  |  | Application under review | [6 empty] | Retrocommission |  |  |  | 10 |  |  |  | Pickup Truck4WD | 16
| 2017-12-01 |  |  | Project approved | [6 empty] | Vehicles |  |  |  | 11 |  |  |  | Pickup TruckAWD | 16
| 2018-12-01 |  | <select one> | Project denied | [6 empty] | Weatherization |  |  |  | 12 |  |  |  | Sport Utility Vehicle or SUV2WD | 21
|  |  | 0 | [7 empty] | Comprehensive | [7 empty] | Sport Utility Vehicle or SUV4WD | 18
|  |  | 1 | [7 empty] | Other | [7 empty] | Sport Utility Vehicle or SUVAWD | 18
2
3
Building stock change pw = DOER |  |  | 4
Calculator Worksheet pw = GC |  |  | 5 | [5 empty] | Resource.Type |  | Site.Type |  | Own.Generation/Site |  | Procuring.Energy.Output | Project.Status
|  |  | 6 | [5 empty] | Solar PV, Roof |  | Municipal Building |  | Y |  | Y - conventional net metered | Complete
Table 6 pw= DOER |  |  | 7 | [5 empty] | Solar PV, Ground |  | School |  | N |  | Y - virtually net metered | Active
|  |  | 8 | [5 empty] | Solar PV, Canopy |  | Private Building |  |  |  |  | Planned
Other tabs pw = GC |  |  | 9 | [5 empty] | Solar Thermal |  | Water/Wastewater Plant |  | Other |  | N | Abandoned
|  |  | 10 | [5 empty] | Wind |  | Brownfield - Landfill |  |  |  | Other
|  |  | 11 | [5 empty] | Wood, Boiler/Furnace |  | Brownfield - Not landfill
|  |  | 12 | [5 empty] | CHP, Gas |  | Greenfield
[9 empty] | CHP, Wood |  | Parking Lot
[9 empty] | Hydro |  | Other
Other

## Reference (hidden)
Conversion Factors
0.003412 | KWH of Electricity to MMBTU
0.1 | Therms to MMBTU
0.139 | Gallons of Fuel Oil to MMBTU
0.091 | Gallons of Propane to MMBTU
0.124 | Gallons of Gasoline to MMBTU
0.139 | Gallons of Diesel to MMBTU
GHG Emissions Conversions | [6 empty] | kBtu Conversions
Fuel | CO2 Emissions Factor (lbs CO2/unit) | CO2 Emissions Factor (metric tonnes CO2/unit) | GHG Emissions Factor (lbs CO2e/unit) | GHG Emissions Factor (Metric Tons CO2e/unit) | Reference for GHG emissions | Reference for CO2 emissions | kBtu Conversion Factor | Reference for kBtu conversion
Grid Electricity CY2001 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.1892 | 0.00053934 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2002 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.1989 | 0.00054373 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2003 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.2505 | 0.00056714 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2004 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.2183 | 0.00055251 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2005 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.2193 | 0.00055299 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2006 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.0848 | 0.00049198 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2007 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.108 | 0.00050252 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2008 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.0224 | 0.00046368 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2009 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.9572 | 0.00043411 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2010 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.96344 | 0.00043693 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2011 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.834 | 0.00037823 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2012 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.834 | 0.00037823 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2013 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.834 | 0.00037823 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity CY2014 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.834 | 0.00037823 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2002 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.1941 | 0.00054154 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2003 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.2247 | 0.00055543 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2004 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.2344 | 0.00055982 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2005 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.2188 | 0.00055275 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2006 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.1521 | 0.00052248 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2007 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.0964 | 0.00049725 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2008 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 1.0652 | 0.0004831 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2009 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.98981 | 0.00044889 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2010 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.96032 | 0.00043552 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2011 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.89872 | 0.00040758 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2012 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.89872 | 0.00040758 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2013 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.89872 | 0.00040758 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Grid Electricity FY2014 | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | 0.89872 | 0.00040758 | MA-based combo from MassDEP based on GHG inventory |  | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Natural Gas (therms) | 11.6977 | 0.0053051 | 11.7286 | 0.0053191 | http://www.energystar.gov/ia/business/evaluate_performance/Emissions_Supporting_Doc.pdf | http://www.eia.gov/oiaf/1605/coefficients.html | 100 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Natural Gas (CCF) | 11.9668 | 0.0054271 | 11.9984 | 0.0054414 | calculated based off of 1 CCF=1.023 therms | calculated based off of 1 CCF=1.023 therms | 102.3 | http://www.eia.gov/tools/faqs/faq.cfm?id=45&t=8
Oil #2/ Diesel for Buildings (gallons) | 22.3769 | 0.010148 | 22.494 | 0.010201 | http://www.energystar.gov/ia/business/evaluate_performance/Emissions_Supporting_Doc.pdf | http://www.eia.gov/oiaf/1605/coefficients.html | 138.6905 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Oil #4 (gallons) | 22.3769 | 0.010148 | 22.494 | 0.010201 | http://www.energystar.gov/ia/business/evaluate_performance/Emissions_Supporting_Doc.pdf | http://www.eia.gov/oiaf/1605/coefficients.html | 138.6905 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Oil #6 (gallons) | 26.0146 | 0.011798 | 26.1416 | 0.011856 | http://www.energystar.gov/ia/business/evaluate_performance/Emissions_Supporting_Doc.pdf | http://www.eia.gov/oiaf/1605/coefficients.html | 149.6905 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
On-Site CHP Electricity (kWh) | 0 | 0 | 0 | 0 | 0 | 0 | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
On-Site Hydro (kWh) | 0 | 0 | 0 | 0 | 0 | 0 | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
On-Site Solar PV Electricity (kWh) | 0 | 0 | 0 | 0 | 0 | 0 | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
On-Site Wind Electricity (kWh) | 0 | 0 | 0 | 0 | 0 | 0 | 3.412 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Electric Vehicles (kWh) | MassDEP factor calculated CO2e | MassDEP factor calculated CO2e | same as Grid Electricity | same as Grid Electricity | MA-based combo from MassDEP based on GHG inventory | 0 | 0 | 0
Diesel Vehicles (gallons) | 22.3769 | 0.010148 | 22.3769 | 0.010148 | based on CO2 number, followed guidance from Sharon Webber (DEP) on non-CO2 emissions based on mobile sector of MA GHG emissions total | http://www.eia.gov/oiaf/1605/coefficients.html | 138.6905 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
E-85, Ethanol-85 (gallons) | 2.9542 | 0.0013398 | 2.9542 | 0.0013398 | based on CO2 number, followed guidance from Sharon Webber (DEP) on non-CO2 emissions based on mobile sector of MA GHG emissions total | http://www.eia.gov/oiaf/1605/coefficients.html | 84.8333 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Gasoline (gallons) | 19.6432 | 0.0089085 | 19.6432 | 0.0089085 | based on CO2 number, followed guidance from Sharon Webber (DEP) on non-CO2 emissions based on mobile sector of MA GHG emissions total | http://www.eia.gov/oiaf/1605/coefficients.html | 125.0714 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Propane (gallons) | 12.6545 | 0.005739 | 12.7829 | 0.0057972 | http://www.energystar.gov/ia/business/evaluate_performance/Emissions_Supporting_Doc.pdf | http://www.eia.gov/oiaf/1605/coefficients.html | 91.3333 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Propane (gallons) Vehicles | 12.6545 | 0.005739 | 12.6545 | 0.005739 | http://www.energystar.gov/ia/business/evaluate_performance/Emissions_Supporting_Doc.pdf | http://www.eia.gov/oiaf/1605/coefficients.html | 91.3333 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Jet Fuel (gallons) | 21.0983 | 0.0095684 | 21.0983 | 0.0095684 | based on CO2 number, followed guidance from Sharon Webber (DEP) on non-CO2 emissions based on mobile sector of MA GHG emissions total | http://www.eia.gov/oiaf/1605/coefficients.html | 127.5 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Used Vegetable Oil | 0 | 0 | 0 | 0 | 0 | 0 | 120 | http://www.theclimateregistry.org/downloads/2012/01/2012-Climate-Registry-Default-Emissions-Factors.pdf
Biodiesel (B100) (gallons) | 0 | 0 | 0 | 0 | http://www.eia.gov/oiaf/1605/coefficients.html | http://www.eia.gov/oiaf/1605/coefficients.html | 127.5952 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Biodiesel (B20) (gallons) | 17.9016 | 0.0081186 | 17.9016 | 0.0081186 | based on CO2 number, followed guidance from Sharon Webber (DEP) on non-CO2 emissions based on mobile sector of MA GHG emissions total | http://www.eia.gov/oiaf/1605/coefficients.html | 136 | Calculated based on B100+diesel, did not round to give Bio credit
Biodiesel (B5) (gallons) | 21.2526 | 0.0096384 | 21.2526 | 0.0096384 | based on CO2 number, followed guidance from Sharon Webber (DEP) on non-CO2 emissions based on mobile sector of MA GHG emissions total | http://www.eia.gov/oiaf/1605/coefficients.html | 138 | Calculated based on B100+diesel, did not round to give Bio credit
CNG (gallons) | 15.2197 | 0.0069023 | 15.2197 | 0.0069023 | based on CO2 number, followed guidance from Sharon Webber (DEP) on non-CO2 emissions based on mobile sector of MA GHG emissions total | http://www.theclimateregistry.org/downloads/2013/01/2013-Climate-Registry-Default-Emissions-Factors.pdf; 1 Gallon Gasoline Equivalent = 126.67 SCF- CNG is typically sold in GGE instead of SCF | 22.453 | http://www.afdc.energy.gov/pdfs/afv_info.pdf
LNG (gallons) | 9.8326 | 0.0044592 | 9.8326 | 0.0044592 | based on CO2 number, followed guidance from Sharon Webber (DEP) on non-CO2 emissions based on mobile sector of MA GHG emissions total | http://www.theclimateregistry.org/downloads/2013/01/2013-Climate-Registry-Default-Emissions-Factors.pdf | 84.82 | http://www.afdc.energy.gov/pdfs/afv_info.pdf
Purchased Steam (mlbs) | EPA only calculated CO2e for district steam | EPA only calculated CO2e for district steam | 207.8218 | 0.09425 | http://www.energystar.gov/ia/business/evaluate_performance/Emissions_Supporting_Doc.pdf | based on ave of Boston & Cambridge calculated data T:\LBE\Agency-Campus Energy-GHG Tracking & Reporting\LBE Database\Account Updates from Agency\Steam | 1194 | https://www.energystar.gov/ia/business/tools_resources/target_finder/help/Energy_Units_Conversion_Table.htm
Coal (tons) | 4152.3288 | 1.8831 | 4192.1653 | 1.9012 | http://www.energystar.gov/ia/business/evaluate_performance/Emissions_Supporting_Doc.pdf | http://www.eia.gov/oiaf/1605/coefficients.html | 20191.5 | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Wood Pellets (tons) | 0 | 0 | 0 | 0 | based upon guidance from Dwayne Breger & Rob Rizzo | based upon guidance from Dwayne Breger & Rob Rizzo | 16500 | www.eia.gov/neic/experts/heatcalc.xls
Cord Wood (chord) | 0 | 0 | 0 | 0 | based upon guidance from Dwayne Breger & Rob Rizzo | based upon guidance from Dwayne Breger & Rob Rizzo | 22000 | www.eia.gov/neic/experts/heatcalc.xls
How to calculate Energy Use Intensity (EUI) for a building/s: add up all kBtu totals for all building/s energy consumption and divide by the building or site square footage.
Energy Efficiency Equivalencies
Fuel | Equivalency Factor (divide by factor) | Reference to calculate equivalents | Comments
MA Homes powered by Electricity per year (kWh) CY2012 | 7600 | US EIA 2011 data for Mass., with corroboration from MassDOER on kWh and therms; DOER data for heating oil
MA Homes heated by Natural Gas per year (therms) CY2012 | 943
MA Homes heated by Oil per year (gallons) CY2012 | 800
MA Homes total energy use (MMBtu) CY2012 | 129
MA Homes powered by Electricity per year (kWh) CY2011 | 7200 | US EIA 2010 data for Mass., with corroboration from MassDOER on kWh and therms; DOER data for heating oil
MA Homes heated by Natural Gas per year (therms) CY2011 | 1020
MA Homes heated by Oil per year (gallons) CY2011 | 800
MA Homes total energy use (MMBtu) CY2011 | 131.2
U.S. Vehicle GHG emissions per year | 4.75 | http://www.epa.gov/cleanenergy/energy-resources/refs.html#vehicles | Formula allows for MA specific number in the future if interested
If colored green, please edit upon release of updated numbers
Terms of Art
Use: | Instead of:
Clean Energy | Green
Combined Heat and Power (CHP) | Co-generation
Wind Turbines | Windmills
Ground Source Heat Pumps (GSHP) | Geothermal
Massachusetts Homes for electricity and gas equivalences
National car equivalencies
MA Capacity Factors
Renewable | Factor | Reference
Solar Capacity | 0.13 | Class I Regulations
Wind Capacity, land-based | 0.26
Wind Capacity, offshore | 0.38
Energy Efficiency Equivalencies
Unit | Factor (Multiply by factor) | Resulting Unit
short ton | 1.1023 | metric ton
Megawatt (MW) | 1000 | kilowatts (kW)
kilowatts (kW) | 8760 | kilowatt hours (kWh)
Gigawatt (GW) | 1000000 | kilowatts (kW)
therm | 100 | kBtu
kBtu | 1000 | Btu
MMBtu | 1000000 | Btu
MMBtu | 10 | therm
Fuel | Factor | Unit | Reference
Petroleum (barrel (bbl)) | 42 | U.S. gallons (gal) | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Coal (1 short ton) | 2000 | pounds (lb) | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Coal (1 long ton) | 2240 | pounds (lb) | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
Coal (1 metric ton) | 1000 | kilograms (kg) | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
wood (1 cord (cd)) | 1.25 | short tons | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
wood (1 cord (cd)) | 128 | cubic feet (ft3) | http://www.eia.gov/totalenergy/data/annual/pdf/sec12.pdf
CO2 (1 metric ton) | 2205 | pounds (lb)